## timesheet
Date and Time	Time	Activity
Week of June 24 / - Note was not keeping great track of my time and on what, was just getting started	8 hours	- ran on assumptions of the product we are creating / - created software construction to create and test packet passing between a controlling software package, i.e. the customer’s interface and the interfaces for the Meerstetter TECs and the Huber chiller / - the software has the phy later abstracted, I used UDP sockets to test basic packet passing / - I verified the software can handle one of each protocol’s message
07/01/19	4 hours	Worked with Bob / - installed DSD Tech SH-U12 RS4845 to TT adapters onto two Arduino boards and tried to get simple RS485 packet passing working – no success / Worked on the software base / - moved *.cpp files into ./src directories, moved .h files in ./h directories / - made proper make files
07/02/2019 / 5pm – 10pm	5 hours	Repo update / - updating repository with changes from 7/1 / Software update / - tried to port/use the Meerstetter packet handling software, due to Arduino IDE strangeness was unable to / - spent 2 hours experimenting with long packet and RS435, found out why the meerstetter packet handling is the way it is, RW485 is a stream protocol, no OS on uC, application must be stateful when reading packets / Hardware / - Bob got the RS485 adapters working between Arduinos
July 3 – 6 no work
July 7 12:30pm start	5 hours	Getting the Meerstetter packet handling working on Arduino. / - had to put all the files into one source and one header file .. WTF ? / - got the meerstetter code passing packets from Ardiono to another over the RS485 adapters, used some private code to mirror packets back to the meerstetter device
July 8 6:30 – 8:30	2 hours	Worked with Bob / - got communication working with real Meerstetter device / - test set and get
July8 9 – 11	2 hours	First thoughts/design of three state machines targeted towards start up and running / - set TEC temps / - start up / - running
07/09/19	1.5 hours	Drew State Machine 0.1.odg for review before implementing
07/13/19	4 hours	Got the meerstetter class completed and tested.
07/16/09	6 hours	start 2pm / - tightening up meerstetter packet receive, this is the current version in working directory / - coding changes to communicate with interim chiller / - completing integrating HumidityDebugv2.0 into new process(not started) / - ended up toiling with getting millis(), delay(), and Serial.print to work in my libraries, found this is what needed to be added : / #if defined(ARDUINO) && ARDUINO >= 100 / #include "Arduino.h" / #else / #include "WProgram.h" / #endif
07/18/19	4 hours during day / 4 hours during night	- started work on prototype / - incorporated my libraries for meerstetter comm and chiller comm / - coded up the getStatus and shutDown bits Bob and I have talked about
07/21/19	4 hours	- added helper functions to chiller library / - worked on prototype code
07/22/19	2 hours	- making better interface for Start, Stop, Running for meerstetter and chiller
07/23/19	2 hours	- tried to establish communication with PolyScience chiller – no communication achieved
07/24/19	2 hours	- wrote PolyScience chiller simulator
07/27/19	4 hours	- wrote, tested, debugged Huber chiller library and simulator
07/28/19	4 hours	- worked on main program, getting the flow and logic correct / - toiled with: / - lack of Serial.print when the Wire.h library is started for the I2C for the SH sensor / - unable to get the RS485 working using the RS485 connectivity on the MAXI
07/29/19	3 hours	- got the RS485 working – needed to remove the RS485 adapter card/module when using the RS485 on the Controllino
07/30/19	3 hours	- got the flow of the program ironed out, went over it with Bob / - this version of the flow is outlined in State Machine 0.3.pdf / - we also resolved the Serial.print clip problem observed when loading the Wire.h and SHT sensor libraries – turns out tobe an order of iniitialization problem – need to load Wire.h and SHT libraries BEFORE doing Serial.begin(9600)
08/03/19	6 hours	- working on the first version of the protocol between the control PC and the Conrollino / - got about 1.5 hours of testing the protocol packets in also
08/10/19	6 hours	- working control protocol
08/11/19	4 hours	- integrating control protocol and attempting end to end testing / - hitting problem, unable to add a 3rd RS232
week of 8/12	4 hours	- integration of controlProtocol, testing and debugging / - remember the problem was the array index w/ math in the index needed to be in parenthasis! / - BOOOOOOO!
08/18/19	6 hours	- fixed/improved out controlProtocol protocol / - it was uint16_t for each protocol element, fixred that to be uint8_t where applicable, arrays of uint8_t for floats, and some other information elements / - also fixed the 0xD becoming 0xA problem, turns out we need to run binary mode rather than text mode for serial communication (in text mode, the OS will change \r to \n ) / - fixed some crashes in message handling of messages from control PC
08/20/19	4 hours	- integrated better LCD message handling / - integrated humidity sampling ( use the average of a configurable amount of samples to smooth spikes in humidity)
08/26/19	4 hours	- resolved issues with float conversion in handling set/get chiller setpoint temperature / - resolved similar issues with the TEC get/set temperature / - setup and ran control protocol test (repeatedly issued gets/sets) one command every 2 seconds, test passed where passed means the system did not crash or restart; however ! Did notice some packet drop on commands from PC to controllno

got the above to Bob

09/18/19	3.5 hours	- code clean up / - documented the whole thing / - updated the flow diagram / - created the protocol document (new)
09/28/19	6 hours	- added the digital encoder / - fixed several protocol failures between Conrollino and Huber / - did a lot of testing with the digital encoder / - found that even w/ interrupts off, the twittling of the encoder causes packet drop on all interfaces – debugged this and found there is nothing we can do but firm up the re-transmit scheme between meerstetter and huber during the get status to avoid frivilous shutdowns due to miscommunication / - a log of testing / - running an overnight test of the control protocol
09/29/19	2 hours	added more commands / - startChiller / - stopChiller / - getChillerInfo / - getTECInfo
10/09/19	3 hours	work with Bob on adding a start button / - completed addition of new commands, start chiller, stop chiller, get chiller info, get tec info
10/14/19	4 hours	- resolved problems w/ huber protocol and retries .. again ! / - resolved problems w/ new – simpler design / - testing

10/22/19	1 hour	- code clean up
10/29/19	2 hours	- code to enable control and monitoring of 3 Katmandus .. / - testing of this code too
12/06/19	2 hours	- added the on/off LED control / - added the falt/no-fault LED control / - added code in getStatus() to provide an independent interval for the humidity check – happens more frequently than the chiller and TECs check
12/10/19	4 hours	- added code to disable button ISR while in high humidity scenario / - controlProtocol changes to enable Windows USB in our controls program / - use Windows USB / - windows read/write bytes slightly different / - a lot of testing of the Windows USB usage
12/11/19	2 hours	- disable the on/off button during high humidity event / - moved all the state-variable changes to one location for TECs and chiller / - only start TECs if the chiller is running / - stop TECs when stopping the chiller
12/12/19	4 hours	- menu driven control program created and tested
12/17/19	6 hours	Added commands to get / - TEC obj temperature / - chiller obj temperature / Huber control / - fixed defect in set chiller temperature – there was a failure in the translation from float to string, needed to use dtostrf rather than sscanf, uC issue.. / Did a lot of testing !

12/18/19	6 hours	- Added Huber PP commands to the huber control library / - Added PP commands to the huber simulator / - more testing / - still not fucking working 100% / - much multi-scenario testing of LEDs versus chiller and TEC states
12/19/19	4 hours	- finished debugging and testing the huber PP commands / - changed all the wording in the menu application (control application) / - ran through much testing of as many scenarios as possible .. last chance to test !

## notes
Arduino MEGA / RX0 pin 11 / TX0 pin 10 / Arduino / RX0 pin 11 / TX0 pin 10